## ListOfFeatures
Product Backlog - Co living (List of your features)
User Stories / List of features
As a stafff, i am able to login and check messages, create contracts, edit and delete.
As a site visitor, I have the possibility to contact for more information.
As a site visitor, i am able to send a request to apply for an apartment.
As a site visitor, I am able to subscribe to newsletters to remain upto date.
As a site visitor i can send a request to terminate my agreement

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
Intial start
Making universal Header and footer |  | Suraj | Completed
Designing database |  | Everyone | Completed
create github repo |  | Sandu | Completed
Scrum editing and uploading |  | Vignesh | Completed
Database tasks
Making Apartment database table |  | Suraj | Completed
Making Contract Database table |  | Sandu | Completed
Making Customer Database table |  | Vignesh | Completed
Edit database design |  | Everyone | completed
Github
Adding collabarators to github |  | Sandu | Completed
Creating github pages |  | Sandu | Completed
Re-editig website layout as per new new features |  | Everyone | Completed
Correcting css part |  | Everyone | Completed
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
Planning features
Discussed about java script features can be added |  | Everyone | Completed
Planning Database table functionality |  | Everyone | Completed
Divided java script features |  | Everyone | Completed
Scrum editing and uploading |  | Vignesh | Completed
Add to database page
Making Add Apartment page with php |  | Suraj | Completed
Making Add Contract page with php |  | Sandu | Completed
Making Add Customer page with php |  | Vignesh | Completed
Testing add page with database |  | Everyone | Completed
Retrieve database
Apartment list data page |  | Suraj | Completed
contract list data page |  | Sandu | Completed
Customer list data page |  | Vignesh | Completed
Testing list page with database |  | Everyone | Completed
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
Delete database
Customer data deleting |  | Vignesh | Completed
Apartment data deleting |  | Suraj | Completed
Contract data deleting |  | Sandu | Completed
Testing delete functionality |  | Everyone | Completed
Updating database
Customer data updating fuctionality |  | Vignesh | Completed
Apartment data updating fuctionality |  | Suraj | Completed
Contract data updating functionality |  | Sandu | Completed
Testing update functionality |  | Everyone | Completed
Javascript functionalities
Image zoom javascript |  | Suraj | Completed
Changing theme color in home java script |  | Sandu | Completed
Scroll to top java script |  | Vignesh | Completed
Form validation |  | Everyone | Completed
Additional tasks
Contact form responses to database |  | Vignesh | Completed
Contact form read page |  | Sandu | Completed
Login page-logout functionality |  | Suraj | Completed
Staff table |  | Sandu | Completed
Final steps
Testing every page and functionality |  | Everyone | Completed
Updating scrum |  | Vignesh | Completed
Adding project to shell.hamk.fi |  | Sandu | Completed
Final testing in shell.hamk.fi |  | Everyone
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.